## Project Plan
Seafarer PMS — Full Migration & V2 Architecture Project Plan
Starting Fresh — 4-Week Plan with Testing
# | Step | Module / Task | Sub-Tasks | Week | Days | Dependencies | Deliverables | Testing | Status
STEP 1: LEGACY IDENTITY RESTRUCTURING — UUID Migrations for All Modules
1.1 | Step 1 | Vessels — UUID Migration | Phase 1: Add vuuid column (TEXT NOT NULL UNIQUE) with backfill using gen_random_uuid() Phase 2: Add FK constraints from all child tables referencing vessels to vessels(vuuid) Phase 3: Refactor all server & frontend code to use vuuid for lookups Phase 4: Convert vessels.id from TEXT to SERIAL PRIMARY KEY | W1 | 1.5 | None — starting module | vuuid column live, ~43 child table FKs, all code uses vuuid, id is SERIAL | Verify all vessel CRUD, child table inserts, frontend navigation | Not Started
1.2 | Step 1 | Components — UUID Migration | Phase 1: Add cuuid column (TEXT NOT NULL UNIQUE) with backfill Phase 2: Add FK constraints from ~15 child tables to components(cuuid) Phase 3: Refactor server & frontend code to use cuuid Phase 4: Convert components.id from TEXT to SERIAL PRIMARY KEY | W1 | 1.5 | Vessels migration complete | cuuid column live, 15 child table FKs, all code uses cuuid, id is SERIAL | Verify component CRUD, spare links, documents, running hours refs | Not Started
1.3 | Step 1 | Jobs — UUID Migration | Phase 1: Add juuid column (TEXT NOT NULL UNIQUE) with backfill Phase 2: Add FK constraints from child tables (job_component_links, work_orders, etc.) to jobs(juuid) Phase 3: Refactor server & frontend code to use juuid Phase 4: Convert jobs.id from TEXT to SERIAL PRIMARY KEY | W1 | 1 | Components migration complete | juuid column live, ~4 child table FKs, all code uses juuid, id is SERIAL | Verify job CRUD, job-component links, work order creation | Not Started
1.4 | Step 1 | Work Orders — UUID Migration | Phase 1: Add wouuid column (TEXT NOT NULL UNIQUE) with backfill Phase 2: Add FK constraints from 4 child tables (executions, execution_details, etc.) to work_orders(wouuid) Phase 3: Refactor server & frontend code to use wouuid Phase 4: Convert work_orders.id from TEXT to SERIAL PRIMARY KEY | W1 | 1 | Jobs migration complete | wouuid column live, 4 child table FKs, all code uses wouuid, id is SERIAL | Verify WO CRUD, execution records, status recalculation, auto-generation | Not Started
1.T1 | Step 1 | TESTING CHECKPOINT — Core Modules | Integration testing across Vessels, Components, Jobs, Work Orders Verify FK constraint integrity across all child tables Test bulk import with new UUID-based identities Validate auto-generation scheduler with SERIAL ids | W1 | 0.5 | Tasks 1.1–1.4 complete | All 4 core modules passing integration tests | End-to-end: create vessel → component → job → work order flow | Not Started
1.5 | Step 1 | Running Hours — UUID Migration | Phase 1: Add rhuuid column to running_hours_audit & component_running_hours_log Phase 2: Add FK constraints to child/related tables Phase 3: Refactor server & frontend code to use rhuuid Phase 4: Convert id to SERIAL PRIMARY KEY | W2 | 0.5 | Components migration complete | rhuuid column live, FK constraints, code refactored, id is SERIAL | Verify RH CRUD, delta propagation, counter types (MASTER/INHERITED) | Not Started
1.6 | Step 1 | Spares — UUID Migration | Phase 1: Add suuid column to spares table with backfill Phase 2: Add FK constraints from spare_component_links, spare_location_stock, spares_history, inventory_transactions Phase 3: Refactor server & frontend code to use suuid Phase 4: Convert spares.id to SERIAL PRIMARY KEY | W2 | 1 | Components migration complete | suuid column live, FK constraints on child tables, code refactored, id is SERIAL | Verify spares CRUD, component links, location stock, inventory transactions | Not Started
1.7 | Step 1 | Defects — UUID Migration | Phase 1: Add duuid column to defects table with backfill Phase 2: Add FK constraints from defect_actions, defect_attachments, recurring_defect_links Phase 3: Refactor server & frontend code to use duuid Phase 4: Convert defects.id to SERIAL PRIMARY KEY | W2 | 1 | Vessels, Components migrations complete | duuid column live, FK constraints, code refactored, id is SERIAL | Verify defect CRUD, actions, attachments, recurring defects, SIRE VIQ | Not Started
1.8 | Step 1 | Certificates & Surveys — UUID Migration | Phase 1: Add certuuid/survuuid columns to certificates & surveys tables Phase 2: Add FK constraints to related tables Phase 3: Refactor server & frontend code to use UUID lookups Phase 4: Convert id columns to SERIAL PRIMARY KEY | W2 | 0.5 | Vessels migration complete | UUID columns live, FK constraints, code refactored, ids are SERIAL | Verify cert/survey CRUD, admin module, category/group management | Not Started
1.T2 | Step 1 | TESTING CHECKPOINT — Extended Modules | Integration testing: Running Hours, Spares, Defects, Certificates/Surveys Verify cross-module FK integrity (e.g., spare-component links, defect-vessel links) Regression testing on core modules (Vessels, Components, Jobs, WOs) | W2 | 0.5 | Tasks 1.5–1.8 complete | All 8 modules passing integration tests with UUID identities | Cross-module flows: component with spares, WO with defects | Not Started
1.9 | Step 1 | Leaf Node Tables — UUID + SERIAL | Add UUID columns and convert id to SERIAL for all remaining leaf tables: - change_request, change_request_attachment, change_request_comment - import_history, import_change_log, bulk_import_history, bulk_import_errors - audit_log, alert_policies, alert_events, alert_deliveries, alert_config - fleet tables, equipment_categories, locations, master_data - form_definitions, form_versions, form_version_usage - ihm_items, ihm_maintenance_log, makers, maker_list, sfi_details, pms_vessel_settings | W2 | 1 | All parent module migrations complete | All leaf tables have UUID columns, all ids are SERIAL auto-increment | Verify each leaf table CRUD, FK integrity with parent tables | Not Started
1.10 | Step 1 | Add Audit Columns to All Tables | Add created_at (TIMESTAMP DEFAULT NOW()), updated_at (TIMESTAMP DEFAULT NOW()) Add created_by (TEXT), updated_by (TEXT) to all tables Update server code to populate audit columns on create/update operations Add database trigger or application logic for auto-updating updated_at | W2 | 1 | Leaf node tables complete (1.9) | All tables have 4 audit columns, server code populates them consistently | Verify audit columns populated on create/update for each module | Not Started
M1 |  | MILESTONE: Step 1 Complete — All Legacy Identity Restructured | All modules have UUID canonical identifiers All ids are SERIAL auto-increment All audit columns in place Full regression test pass | W2 | 0.5 | All Step 1 tasks | Fully restructured legacy database with UUID identities and audit trail | Full regression testing — all modules end-to-end | Not Started
STEP 2: V2 ARCHITECTURE — Build V2 Modules for All Domains
2.1 | Step 2 | V2 — Components + Bulk Upload Module | Create server/v2/components/ with repository-service-controller-routes layers Create server/v2/bulk/ for bulk upload functionality Define V2 schemas in shared/v2/components/schema.ts and shared/v2/bulk/schema.ts Wire frontend URL builders + toggle mechanism All CRUD operations: list, create, read, update, delete components Bulk import with dry-run, preview, apply workflow | W3 | 1.5 | Step 1 complete (M1) | V2 Components + Bulk module fully operational, toggle working | Side-by-side comparison: legacy vs V2 returns same data | Not Started
2.2 | Step 2 | V2 — Jobs Module | Create server/v2/jobs/ with 4-layer architecture Re-export component schemas from V2 components module Implement job CRUD, job-component linking, maintenance history Wire frontend URL builders + toggle | W3 | 0.5 | V2 Components (2.1) | V2 Jobs module operational, toggle working | Verify job-component links, work order references | Not Started
2.3 | Step 2 | V2 — Work Orders Module | Create server/v2/work-orders/ with 4-layer architecture Re-export from components + jobs + spares schemas Implement WO CRUD, execution records, status computation Auto-generation scheduler, status recalculator Wire frontend URL builders + toggle | W3 | 1 | V2 Jobs (2.2) | V2 Work Orders module operational with automation services | Verify WO lifecycle, auto-generation, status recalc | Not Started
2.4 | Step 2 | V2 — Spares + Stores Module | Create server/v2/spares/ and server/v2/stores/ with 4-layer architecture Re-export component schemas Implement spare CRUD, component links, location stock, inventory transactions Stores module: items, ledger Wire frontend URL builders + toggle | W3 | 1 | V2 Components (2.1) | V2 Spares + Stores modules operational | Verify spare-component links, inventory, location stock sync | Not Started
2.5 | Step 2 | V2 — Running Hours Module | Create server/v2/running-hours/ with 4-layer architecture Re-export component schemas Implement RH CRUD, delta propagation, counter types (MASTER/INHERITED/NOT_RH_DRIVEN) Wire frontend URL builders + toggle | W3 | 0.5 | V2 Components (2.1) | V2 Running Hours module operational | Verify counter propagation, audit trail, safety validations | Not Started
2.T1 | Step 2 | TESTING CHECKPOINT — Core V2 Modules | Side-by-side comparison: legacy vs V2 for core modules Toggle testing: switch between legacy/V2 and verify same behavior Cross-module V2 flows: create component → job → WO → execution | W3 | 0.5 | Tasks 2.1–2.5 complete | Core V2 modules verified, toggle working | Complete V2 core regression suite | Not Started
2.6 | Step 2 | V2 — Defects Module | Create server/v2/defects/ with 4-layer architecture Implement defect CRUD, actions, attachments, recurring defects SIRE VIQ 7 integration, target date extension workflow Condition of Class tracking Wire frontend URL builders + toggle | W4 | 1 | V2 Components (2.1) | V2 Defects module operational with all workflows | Verify defect lifecycle, recurring defects, VIQ integration | Not Started
2.7 | Step 2 | V2 — Certificates & Surveys Module | Create server/v2/certificates/ with 4-layer architecture Implement cert/survey CRUD, admin 3-tab interface Configurable categories/groups, prefixed ID formats Wire frontend URL builders + toggle | W4 | 0.5 | Step 1 Certs migration complete | V2 Certificates module operational | Verify cert CRUD, category management, survey workflows | Not Started
2.8 | Step 2 | V2 — Admin, Change Requests, Fleet, Forms | Create V2 modules for remaining domains: - Admin: bulk import, data purging, Fleet Admin Dashboard - Change Requests: workflow with apply-approved-changes - Fleet: vessel mapping, component mapping, spare mapping - Forms: form definitions, versions, usage Wire frontend URL builders + toggle for each | W4 | 1 | Core V2 modules (2.1–2.7) | All supporting V2 modules operational | Verify admin operations, change request workflow, fleet mappings | Not Started
2.T2 | Step 2 | TESTING CHECKPOINT — All V2 Modules | Side-by-side comparison: legacy vs V2 for every module Toggle testing for Defects, Certs, Admin modules Performance comparison: V2 vs legacy response times | W4 | 0.5 | All Step 2 tasks complete | All V2 modules verified, toggle working for every module | Complete V2 regression suite, performance benchmarks | Not Started
M2 |  | MILESTONE: Step 2 Complete — Full V2 Architecture Built | Every legacy module has a V2 counterpart Frontend toggle works for all modules Side-by-side verification passed | W4 | 0 | All Step 2 tasks + testing | Complete V2 architecture running alongside legacy | Sign-off on V2 parity with legacy | Not Started
STEP 3: CUTOVER — Default to V2, Test, Remove Legacy
3.1 | Step 3 | Default API to V2 | Change getApiMode() default from "legacy" to "v2" Keep toggle available for rollback Monitor for issues Update all documentation to reflect V2 as default | W4 | 0.5 | All V2 modules verified (M2) | V2 is the default API for all users, legacy available via toggle | Smoke test all modules in V2 default mode | Not Started
3.2 | Step 3 | Stabilization & Full Regression Testing | Run full regression test suite with V2 as default Fix any bugs discovered during stabilization Performance testing under V2 User acceptance testing period | W4 | 1 | V2 set as default (3.1) | V2 stable with no critical bugs, performance validated | Full regression, UAT, performance benchmarks | Not Started
3.3 | Step 3 | Remove Legacy Code | Remove legacy route registrations from server/routes.ts Remove legacy services from server/services/ Remove toggle mechanism (useApiVersion hook, ComponentApiToggle) Simplify *ApiV2.ts files to only return V2 URLs Clean up shared/schema.ts — remove legacy-only types Remove legacy storage interface (server/storage.ts) Optional: Rename /technical/api/v2/ to /technical/api/ | W4 | 1 | Stabilization passed (3.2) | Codebase contains only V2 architecture, no legacy code | Full regression on clean V2 codebase | Not Started
3.4 | Step 3 | Final End-to-End Testing & Sign-Off | Complete end-to-end testing of entire application Verify all modules: Vessels, Components, Jobs, WOs, RH, Spares, Defects, Certs Verify admin operations, bulk import, fleet management Verify RBAC for Ship/Office/PMS Admin roles Database integrity verification Documentation review and update | W4 | 0.5 | Legacy removal (3.3) | Production-ready V2-only codebase | Complete test suite passing, documentation current | Not Started
M3 |  | MILESTONE: Project Complete — V2 Architecture Live | All legacy code removed V2 architecture is sole codebase All UUID identities in place All audit columns active Full test coverage | W4 | 0 | All tasks complete | Production-ready Seafarer PMS with V2 architecture | Final sign-off | Not Started

## Weekly Summary
Weekly Summary — Task Distribution
Week | Focus Area | Key Tasks | Days Used | Cumulative Days | Notes
Week 1 (Days 1-5) | Core Module Migrations (Vessels → Components → Jobs → WOs) | 1.1 Vessels UUID (4 phases) — 1.5 days 1.2 Components UUID (4 phases) — 1.5 days 1.3 Jobs UUID (4 phases) — 1 day 1.4 Work Orders UUID (4 phases) — 1 day 1.T1 Testing Checkpoint: Core Modules — 0.5 day | 5.5 | 5.5 | Start with foundation modules Each module follows proven 4-phase pattern Pattern speeds up after first module
Week 2 (Days 6-10) | Extended Module Migrations + Leaf Tables + Audit Columns | 1.5 Running Hours UUID — 0.5 day 1.6 Spares UUID — 1 day 1.7 Defects UUID — 1 day 1.8 Certificates/Surveys UUID — 0.5 day 1.T2 Testing Checkpoint: Extended Modules — 0.5 day 1.9 Leaf Node Tables UUID + SERIAL — 1 day 1.10 Audit Columns on All Tables — 1 day M1 Step 1 Milestone — 0.5 day | 6 | 11.5 | Faster pace — pattern is established Step 1 fully complete by end of Week 2
Week 3 (Days 11-15) | V2 Architecture Build (Core Modules) | 2.1 V2 Components + Bulk Upload — 1.5 days 2.2 V2 Jobs — 0.5 day 2.3 V2 Work Orders — 1 day 2.4 V2 Spares + Stores — 1 day 2.5 V2 Running Hours — 0.5 day 2.T1 Testing Checkpoint: Core V2 — 0.5 day | 5 | 16.5 | V2 modules follow established 4-layer pattern Includes toggle mechanism + frontend wiring
Week 4 (Days 16-20) | V2 Extended Modules + Cutover + Legacy Removal | 2.6 V2 Defects — 1 day 2.7 V2 Certificates/Surveys — 0.5 day 2.8 V2 Admin + Supporting — 1 day 2.T2 Testing Checkpoint: All V2 — 0.5 day 3.1 Default to V2 — 0.5 day 3.2 Stabilization & Full Regression — 1 day 3.3 Remove Legacy Code — 1 day 3.4 Final E2E Testing & Sign-off — 0.5 day | 6 | 22.5 | Tight schedule — may need buffer days V2 modules faster with pattern established Legacy removal is final step

## Migration Pattern
4-Phase UUID Migration Pattern — Applied to Each Module
Phase | Name | What It Does | SQL Pattern | Verification
1 | Add UUID Column | Add a TEXT NOT NULL UNIQUE column (e.g., vuuid, cuuid) Backfill existing rows with gen_random_uuid() Use safe pattern: nullable → populate → NOT NULL → UNIQUE | ALTER TABLE <table> ADD COLUMN <uuid> TEXT; UPDATE <table> SET <uuid> = gen_random_uuid(); ALTER TABLE <table> ALTER COLUMN <uuid> SET NOT NULL; ALTER TABLE <table> ADD CONSTRAINT <uuid>_unique UNIQUE (<uuid>); | Column exists, NOT NULL, UNIQUE All rows have UUID values No duplicates
2 | Add FK Constraints | Add FOREIGN KEY constraints from child tables to parent(uuid) Child tables store UUID from parent.uuid column Ensures referential integrity at DB level | ALTER TABLE <child> ADD CONSTRAINT <fk_name> FOREIGN KEY (<ref_col>) REFERENCES <parent>(<uuid>); | FK constraints visible in information_schema Child inserts fail if parent UUID missing Cascade behavior works
3 | Refactor Code | Update all server lookups to use eq(table.uuid, value) Update frontend navigation to use uuid Update API routes to accept uuid params Remove id-based lookups everywhere | Server: eq(table.uuid, value) instead of eq(table.id, value) Frontend: /module/:uuid instead of /module/:id API: POST body uses uuid for references | grep finds no old id-based lookups Frontend URLs use uuid All CRUD operations work with uuid
4 | Convert id to SERIAL | Drop old TEXT PRIMARY KEY Add SERIAL (auto-increment integer) PRIMARY KEY Remove any old ID generation logic (e.g., WO-xxx) | ALTER TABLE <table> DROP CONSTRAINT <table>_pkey; ALTER TABLE <table> DROP COLUMN id; ALTER TABLE <table> ADD COLUMN id SERIAL PRIMARY KEY; | id column is integer type nextval sequence exists Inserts auto-generate id No old ID generation code remains
Module-by-Module Application
Module | UUID Column Name | Estimated Child Tables | Complexity | Est. Days
Vessels | vuuid | ~43 (largest) | High | 2
Components | cuuid | ~15 | High | 2
Jobs | juuid | ~4 | Medium | 1.5
Work Orders | wouuid | 4 | Medium-High | 2
Running Hours | rhuuid | ~2-3 | Low-Medium | 1
Spares | suuid | ~4-5 | Medium | 1.5
Defects | duuid | ~3-4 | Medium | 1.5
Certificates/Surveys | certuuid/survuuid | ~1-2 | Low | 1
Leaf Node Tables | Various | N/A | Medium (volume) | 2

## V2 Architecture
V2 Module Architecture — Build Guide
Module | V2 Path | Schema Re-exports From | Key Endpoints | Dependencies | Est. Days
Components + Bulk | server/v2/components/ server/v2/bulk/ | Root (defines base schemas) | CRUD components, documents, class/regulatory Bulk import: dry-run, preview, apply | None | 2
Jobs | server/v2/jobs/ | Components | CRUD jobs, job-component links Maintenance history | V2 Components | 1
Work Orders | server/v2/work-orders/ | Components + Jobs + Spares | CRUD WOs, executions, execution details Status computation, auto-generation Vessel settings | V2 Jobs | 1.5
Spares + Stores | server/v2/spares/ server/v2/stores/ | Components | CRUD spares, component links, location stock Inventory transactions Stores items + ledger | V2 Components | 1.5
Running Hours | server/v2/running-hours/ | Components | RH audit, component RH log Delta propagation, counter types | V2 Components | 1
Defects | server/v2/defects/ | Components (new) | CRUD defects, actions, attachments Recurring defects, SIRE VIQ Target date extensions | V2 Components | 1.5
Certificates/Surveys | server/v2/certificates/ | Standalone (new) | CRUD certs/surveys Admin categories/groups | None | 1
Admin + Fleet + CR | server/v2/admin/ server/v2/fleet/ server/v2/change-requests/ | Multiple | Fleet admin dashboard, vessel mapping Change request workflow Bulk admin operations | All V2 modules | 1.5
V2 4-Layer Architecture Pattern (Applied to Each Module)
Layer | Name | File Location | Responsibility | Rules
Layer 1 | Repository | server/v2/<module>/repositories/<name>Repository.ts | Direct Drizzle ORM queries via getDb() | Data access only, no business logic
Layer 2 | Service | server/v2/<module>/services/<name>Service.ts | Business logic, validation, orchestration | Calls repositories, enforces rules
Layer 3 | Controller | server/v2/<module>/controllers/<name>Controller.ts | HTTP request/response handling | Parses input, calls services, formats output
Layer 4 | Routes | server/v2/<module>/routes.ts | Express router with asyncHandler wrapper | Maps HTTP methods to controller methods

## Legend & Notes
Legend & Project Notes
Color Legend
Step 1 — Legacy Identity Restructuring
Step 2 — V2 Architecture Build
Step 3 — Cutover & Legacy Removal
Testing Checkpoint
Milestone / Sign-off
Key Project Rules
1. | All schema changes use Drizzle file-based SQL migrations only (drizzle-kit generate)
2. | One logical change per migration file — never batch unrelated changes
3. | Legacy code stays untouched until Step 3 Phase 4 (legacy removal)
4. | V2 modules are additive — they run alongside legacy with frontend toggle
5. | V2 schemas live in shared/v2/<module>/schema.ts, re-export from parent modules
6. | All V2 modules use getDb() from server/db.ts — never use legacy storage interface
7. | Frontend uses URL builder files (*ApiV2.ts) — no hardcoded API paths
8. | UUID columns use TEXT NOT NULL UNIQUE — not actual UUID type
9. | Each module follows the proven 4-phase pattern: UUID → FK → Code Refactor → SERIAL
10. | Audit columns (created_at, updated_at, created_by, updated_by) added after all identity migrations
11. | Testing checkpoints are mandatory between major phases — never skip them
12. | Total estimated timeline: 4 weeks (20 working days) with buffer for overruns
Timeline Summary
Step 1: Legacy Identity Restructuring | ~11.5 days | Weeks 1-2
Step 2: V2 Architecture Build | ~8 days | Weeks 3-4
Step 3: Cutover & Cleanup | ~3 days | Week 4
Testing Checkpoints (included in above) | ~3 days | Spread across all weeks
TOTAL | ~20 working days | 4 weeks