## ag-grid
ID | Vessel | Issue Date | Category | Component | Description | Target Date | Date Compl. | Status | Priority | Actions
D005-26-0001 | Vessel 5 | 2026-02-16 | Defect | Lifeboat and Equipment | It was observed that the Lifeboat hatch was not closing properly and was thus not gas tight. | 2026-05-10 |  | Open | High
D001-26-0001 | Vessel 1 | 2026-02-11 | Defect | Electric Cable installation | Following Condition of Class (Machinery) was issued COC nr. LBN0/2024/XXXX - Temporary repairs on electrical cable pipe ducts on Main Deck to be definitively repaired before the limit date. Due date 27-Jul-2026 | 2026-07-27 |  | Open | High
D002-26-0001 | Vessel 2 | 2026-01-15 | Defect | Windlasses And Winches | Forward winch hydraulic oil reservoir tank gauge glass closing device (bottom) was noted to be leaking approximately a drop every minute and oil could be seen covering one fifth of the area within it's save all. Reportedly the 'O' ring for the coupling was damaged. | 2026-04-16 |  | Open | Medium
D009-26-0002 | Vessel 9 | 2026-01-14 | Defect | Anchors And Chains | One of the stud for the starboard chain locker bulkhead manhole was noted to be broken from the base with part of the stud remaining within the threaded hole. | 2026-03-06 |  | Open | Low
D009-26-0001 | Vessel 9 | 2026-01-07 | Defect | Gyro Plants, Autopilots, Compasses | Gyro compass No 1 was observed to be displaying a persistent error and the heading was about 10° off. | 2026-03-25 | 2026-02-01 | Open | Medium