## Overdue Jobs
SEAFARER TECHNICAL MANAGEMENT SYSTEM
OVERDUE JOBS REPORT
Vessel: Vessel 4 | [11 empty] | Report Date: 04-Feb-2026 09:21
Generated By: PMS System | [11 empty] | Total Records: 144
S.No | Work Order No | Job Title | Comp Code | Component Name | Dept | Due Date | Days Overdue | Next Due RH | Current RH | RH Overdue | Assigned To | Last Done | Critical Equip | Overdue Type
1 | MKR-IN-00045-411.002-2026-001 | [!] Radar Band Parts, Lubrication - 6M | 411.002 | X-Band Radar | Deck | 2026-01-10 | 40378 | - | 20.00 | 0 | 2nd Officer | 10-Jul-2025 | YES | Calendar
2 | MKR-IN-00071-278.010.01-2026-001 | [!] Impressed Current Cathodic Protection (ICCP), Inspection - 1M | 278.010.01 | Impressed Current Systems No.01 | Engine | 2026-01-13 | 39282 | - | 0.00 | 0 | 2nd Engineer | 13-Dec-2025 | YES | Calendar
3 | MKR-SE-00019-411.001-2026-001 | [!] Radar Band Lithium Battery, Renewal/Replace - 3Y | 411.001 | S-Band Radar | Deck | 2026-01-13 | 39282 | - | 100.00 | 0 | 2nd Officer | 13-Jan-2023 | YES | Calendar
4 | MKR-SE-00019-411.002-2026-001 | [!] Radar Band Lithium Battery, Renewal/Replace - 3Y | 411.002 | X-Band Radar | Deck | 2026-01-13 | 39282 | - | 20.00 | 0 | 2nd Officer | 13-Jan-2023 | YES | Calendar
5 | MKR-IN-00073-501.002-2026-001 | [!] Covered (Totally Enclosed) Lifeboats Inspection - 1M | 501.002 | Covered Lifeboats | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | 2nd Engineer | 14-Dec-2025 | YES | Calendar
6 | MKR-IN-00088-665.003-2026-001 | [!] Emergency Generator Drive Units Inspection - 6M | 665.003 | Emergency Generator Drive Units | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | 3rd Engineer | 14-Jul-2025 | YES | Calendar
7 | MKR-IN-00045-411.001-2026-001 | [!] Radar Band Parts, Lubrication - 6M | 411.001 | S-Band Radar | Deck | 2026-01-14 | 38917 | - | 100.00 | 0 | 2nd Officer | 14-Jul-2025 | YES | Calendar
8 | MKR-IN-00071-278.010.02-2026-001 | [!] Impressed Current Cathodic Protection (ICCP), Inspection - 1M | 278.010.02 | Impressed Current Systems No.02 | Engine | 2026-01-18 | 37456 | - | 0.00 | 0 | 2nd Engineer | 18-Dec-2025 | YES | Calendar
9 | MKR-IN-00087-665.001-2026-001 | [!] Emergency Generator Routine Inspection - 1M | 665.001 | Emergency Generator Aggregates, Complete | Engine | 2026-01-20 | 36726 | - | 0.00 | 0 | 3rd Engineer | 20-Jan-2025 | YES | Calendar
10 | MKR-IN-00080-652.002.05-2026-001 | AE Cylinder Covers with Valves Inspection - 1M | 652.002.05 | AE2 Cylinder Covers W/Valves No.05 | Engine | 2026-01-02 | 43300 | - | 0.00 | 0 | 3rd Engineer | 02-Dec-2025 | No | Calendar
11 | MKR-IN-00085-652.003.02-2026-001 | AE Cylinder Liner Inspection - 1M | 652.003.02 | AE2 Cylinder Liners No.02 | Engine | 2026-01-02 | 43300 | - | 0.00 | 0 | 3rd Engineer | 02-Dec-2025 | No | Calendar
12 | MKR-IN-00085-652.003.05-2026-001 | AE Cylinder Liner Inspection - 1M | 652.003.05 | AE2 Cylinder Liners No.05 | Engine | 2026-01-02 | 43300 | - | 0.00 | 0 | 3rd Engineer | 02-Dec-2025 | No | Calendar
13 | MKR-IN-00080-653.002.04-2026-001 | AE Cylinder Covers with Valves Inspection - 1M | 653.002.04 | AE3 Cylinder Covers W/Valves No.04 | Engine | 2026-01-02 | 43300 | - | 0.00 | 0 | 3rd Engineer | 02-Dec-2025 | No | Calendar
14 | MKR-IN-00085-653.003.02-2026-001 | AE Cylinder Liner Inspection - 1M | 653.003.02 | AE3 Cylinder Liners No.02 | Engine | 2026-01-02 | 43300 | - | 0.00 | 0 | 3rd Engineer | 02-Dec-2025 | No | Calendar
15 | MKR-IN-00085-653.003.06-2026-001 | AE Cylinder Liner Inspection - 1M | 653.003.06 | AE3 Cylinder Liners No.06 | Engine | 2026-01-02 | 43300 | - | 0.00 | 0 | 3rd Engineer | 02-Dec-2025 | No | Calendar
16 | MKR-IN-00072-285.001.02-2026-001 | Ballast Tanks Inspection - 1M | 285.001.02 | Ballast Tanks/SW Tanks No.02 | Engine | 2026-01-02 | 43300 | - | 0.00 | 0 | 2nd Engineer | 02-Dec-2025 | No | Calendar
17 | MKR-IN-00076-601.005.03-2026-001 | Main Engine – Connecting Rods, Crosshead & Guide Assemblies Inspection - 1M | 601.005.03 | ME Connecting Rods, Crosshead, Guides No.03 | Engine | 2026-01-02 | 43300 | - | 4020.00 | 0 | 2nd Engineer | 02-Dec-2025 | No | Calendar
18 | MKR-IN-00077-601.018-2026-001 | Main Engine – Crankcase Inspection - 1M | 601.018 | ME Crankcases | Engine | 2026-01-02 | 43300 | - | 4020.00 | 0 | 2nd Engineer | 02-Dec-2025 | No | Calendar
19 | MKR-IN-00079-601.066.04-2026-001 | Main Engine – Indicator Valves & Indicators Inspection - 1M | 601.066.04 | ME Indicators No.04 | Engine | 2026-01-02 | 43300 | - | 4020.00 | 0 | 2nd Engineer | 02-Dec-2025 | No | Calendar
20 | MKR-IN-00055-702.005.02-2026-001 | Purifier, Visual Check - 3M | 702.005.02 | FO Separators No.02 | Engine | 2026-01-05 | 42204 | - | 0.00 | 0 | 3rd Engineer | 05-Oct-2025 | No | Calendar
21 | MKR-OV-00008-712.011.01-2026-001 | Purifier, Overhaul - 6M | 712.011.01 | LO Separators No.01 | Engine | 2026-01-05 | 42204 | - | 0.00 | 0 | 3rd Engineer | 05-Jul-2025 | No | Calendar
22 | MKR-IN-00055-712.011.02-2026-001 | Purifier, Visual Check - 3M | 712.011.02 | LO Separators No.02 | Engine | 2026-01-05 | 42204 | - | 1501.00 | 0 | 3rd Engineer | 05-Oct-2025 | No | Calendar
23 | MKR-IN-00061-721.001.01-2026-001 | Pump General, Routine - 3M | 721.001.01 | Main Sw Cooling Pumps No.01 | Engine | 2026-01-05 | 42204 | - | 0.00 | 0 | 2nd Engineer | 05-Oct-2025 | No | Calendar
24 | MKR-IN-00054-702.005.02-2026-004 | Purifier, Routine - 1W | 702.005.02 | FO Separators No.02 | Engine | 2026-01-08 | 41109 | - | 0.00 | 0 | 3rd Engineer | 2026-01-01 | No | Calendar
25 | MKR-IN-00041-401.005-2026-002 | Rudder, Visual Check - 1M | 401.005 | Rudders W/Nozzle | Engine | 2026-02-08 | 41078 | - | 0.00 | 0 | 2nd Engineer | 2026-01-08 | No | Calendar
26 | MKR-SE-00023-702.010.01-2026-001 | Purifier Gear Pump Bush, Renewal/Replace - 2Y | 702.010.01 | DO Separator Booster Pumps No.01 | Engine | 2026-01-09 | 40743 | - | 0.00 | 0 | 3rd Engineer | 09-Jan-2024 | No | Calendar
27 | MKR-SE-00025-801.001-2026-001 | Ballast Pump Gear Coupling Gear Oil, Renewal - 6M | 801.001 | Clean Ballast Pumps | Engine | 2026-01-10 | 40378 | - | 0.00 | 0 | Chief Engineer | 10-Jul-2025 | No | Calendar
28 | MKR-IN-00057-702.010.02-2026-001 | Purifier Gear Pump Safety Joint, Visual Check - 6M | 702.010.02 | DO Separator Booster Pumps No.02 | Engine | 2026-01-10 | 40378 | - | 0.00 | 0 | 3rd Engineer | 10-Jul-2025 | No | Calendar
29 | MKR-OV-00008-702.005.01-2026-001 | Purifier, Overhaul - 6M | 702.005.01 | FO Separators No.01 | Engine | 2026-01-10 | 40378 | - | 0.00 | 0 | 3rd Engineer | 10-Jul-2025 | No | Calendar
30 | MKR-OV-00008-702.005.02-2026-001 | Purifier, Overhaul - 6M | 702.005.02 | FO Separators No.02 | Engine | 2026-01-10 | 40378 | - | 0.00 | 0 | 3rd Engineer | 10-Jul-2025 | No | Calendar
31 | MKR-IN-00044-403.006.01-2026-001 | Steering Gear Hydraulic Pump, Visual Check - 10Y | 403.006.01 | Hydr. Oil Pumps No.01 | Engine | 2026-01-10 | 40378 | - | 0.00 | 0 | 2nd Engineer | 10-Jan-2016 | No | Calendar
32 | MKR-IN-00056-712.011.01-2026-001 | Purifier Parts, Visual Check - 1Y | 712.011.01 | LO Separators No.01 | Engine | 2026-01-10 | 40378 | - | 0.00 | 0 | 3rd Engineer | 10-Jan-2025 | No | Calendar
33 | MKR-IN-00056-712.011.02-2026-001 | Purifier Parts, Visual Check - 1Y | 712.011.02 | LO Separators No.02 | Engine | 2026-01-10 | 40378 | - | 1501.00 | 0 | 3rd Engineer | 10-Jan-2025 | No | Calendar
34 | MKR-IN-00062-721.001.01-2026-001 | Pump Parts, Inspection - 12M/8000H | 721.001.01 | Main Sw Cooling Pumps No.01 | Engine | 2026-01-10 | 40378 | - | 0.00 | 0 | 2nd Engineer | 10-Jan-2025 | No | Calendar
35 | MKR-SE-00023-702.010.02-2026-001 | Purifier Gear Pump Bush, Renewal/Replace - 2Y | 702.010.02 | DO Separator Booster Pumps No.02 | Engine | 2026-01-11 | 40013 | - | 0.00 | 0 | 3rd Engineer | 11-Jan-2024 | No | Calendar
36 | MKR-SE-00021-712.011.01-2026-001 | Purifier Parts, Renewal/Replace - 2Y | 712.011.01 | LO Separators No.01 | Engine | 2026-01-11 | 40013 | - | 0.00 | 0 | 3rd Engineer | 11-Jan-2024 | No | Calendar
37 | MKR-SE-00021-712.011.02-2026-001 | Purifier Parts, Renewal/Replace - 2Y | 712.011.02 | LO Separators No.02 | Engine | 2026-01-11 | 40013 | - | 1501.00 | 0 | 3rd Engineer | 11-Jan-2024 | No | Calendar
38 | MKR-SE-00022-712.011.02-2026-001 | Purifier Multi Monitor Pressure Sensor, Renewal/Replace - 3Y | 712.011.02 | LO Separators No.02 | Engine | 2026-01-12 | 39648 | - | 1501.00 | 0 | 3rd Engineer | 12-Jan-2023 | No | Calendar
39 | MKR-SE-00020-601.026.03-2026-001 | ME Valves, Renewal/Replace - 5Y | 601.026.03 | ME Hp Fuel Pumps No.03 | Engine | 2026-01-12 | 39648 | - | 4020.00 | 0 | 2nd Engineer | 12-Jan-2021 | No | Calendar
40 | MKR-SE-00020-601.026.04-2026-001 | ME Valves, Renewal/Replace - 5Y | 601.026.04 | ME Hp Fuel Pumps No.04 | Engine | 2026-01-12 | 39648 | - | 4020.00 | 0 | 2nd Engineer | 12-Jan-2021 | No | Calendar
41 | MKR-IN-00080-651.002.03-2026-001 | AE Cylinder Covers with Valves Inspection - 1M | 651.002.03 | AE1 Cylinder Covers W/Valves No.03 | Engine | 2026-01-13 | 39282 | - | 20.00 | 0 | 3rd Engineer | 13-Dec-2025 | No | Calendar
42 | MKR-IN-00080-651.002.06-2026-001 | AE Cylinder Covers with Valves Inspection - 1M | 651.002.06 | AE1 Cylinder Covers W/Valves No.06 | Engine | 2026-01-13 | 39282 | - | 20.00 | 0 | 3rd Engineer | 13-Dec-2025 | No | Calendar
43 | MKR-IN-00085-651.003.03-2026-001 | AE Cylinder Liner Inspection - 1M | 651.003.03 | AE1 Cylinder Liners No.03 | Engine | 2026-01-13 | 39282 | - | 20.00 | 0 | 3rd Engineer | 13-Dec-2025 | No | Calendar
44 | MKR-IN-00085-651.003.05-2026-001 | AE Cylinder Liner Inspection - 1M | 651.003.05 | AE1 Cylinder Liners No.05 | Engine | 2026-01-13 | 39282 | - | 20.00 | 0 | 3rd Engineer | 13-Dec-2025 | No | Calendar
45 | MKR-IN-00080-652.002.02-2026-001 | AE Cylinder Covers with Valves Inspection - 1M | 652.002.02 | AE2 Cylinder Covers W/Valves No.02 | Engine | 2026-01-13 | 39282 | - | 0.00 | 0 | 3rd Engineer | 13-Dec-2025 | No | Calendar
46 | MKR-IN-00080-652.002.06-2026-001 | AE Cylinder Covers with Valves Inspection - 1M | 652.002.06 | AE2 Cylinder Covers W/Valves No.06 | Engine | 2026-01-13 | 39282 | - | 0.00 | 0 | 3rd Engineer | 13-Dec-2025 | No | Calendar
47 | MKR-IN-00085-652.003.03-2026-001 | AE Cylinder Liner Inspection - 1M | 652.003.03 | AE2 Cylinder Liners No.03 | Engine | 2026-01-13 | 39282 | - | 0.00 | 0 | 3rd Engineer | 13-Dec-2025 | No | Calendar
48 | MKR-IN-00080-653.002.01-2026-001 | AE Cylinder Covers with Valves Inspection - 1M | 653.002.01 | AE3 Cylinder Covers W/Valves No.01 | Engine | 2026-01-13 | 39282 | - | 0.00 | 0 | 3rd Engineer | 13-Dec-2025 | No | Calendar
49 | MKR-IN-00080-653.002.06-2026-001 | AE Cylinder Covers with Valves Inspection - 1M | 653.002.06 | AE3 Cylinder Covers W/Valves No.06 | Engine | 2026-01-13 | 39282 | - | 0.00 | 0 | 3rd Engineer | 13-Dec-2025 | No | Calendar
50 | MKR-IN-00085-653.003.05-2026-001 | AE Cylinder Liner Inspection - 1M | 653.003.05 | AE3 Cylinder Liners No.05 | Engine | 2026-01-13 | 39282 | - | 0.00 | 0 | 3rd Engineer | 13-Dec-2025 | No | Calendar
51 | MKR-IN-00072-285.001.01-2026-001 | Ballast Tanks Inspection - 1M | 285.001.01 | Ballast Tanks/SW Tanks No.01 | Engine | 2026-01-13 | 39282 | - | 0.00 | 0 | 2nd Engineer | 13-Dec-2025 | No | Calendar
52 | MKR-IN-00072-285.001.04-2026-001 | Ballast Tanks Inspection - 1M | 285.001.04 | Ballast Tanks/SW Tanks No.04 | Engine | 2026-01-13 | 39282 | - | 0.00 | 0 | 2nd Engineer | 13-Dec-2025 | No | Calendar
53 | MKR-IN-00072-285.001.08-2026-001 | Ballast Tanks Inspection - 1M | 285.001.08 | Ballast Tanks/SW Tanks No.08 | Engine | 2026-01-13 | 39282 | - | 0.00 | 0 | 2nd Engineer | 13-Dec-2025 | No | Calendar
54 | MKR-IN-00072-285.001.09-2026-001 | Ballast Tanks Inspection - 1M | 285.001.09 | Ballast Tanks/SW Tanks No.09 | Engine | 2026-01-13 | 39282 | - | 0.00 | 0 | 2nd Engineer | 13-Dec-2025 | No | Calendar
55 | MKR-IN-00072-285.001.10-2026-001 | Ballast Tanks Inspection - 1M | 285.001.10 | Ballast Tanks/SW Tanks No.10 | Engine | 2026-01-13 | 39282 | - | 0.00 | 0 | 2nd Engineer | 13-Dec-2025 | No | Calendar
56 | MKR-IN-00058-702.010.01-2026-001 | Purifier Gear Pump, Visual Check - 1Y | 702.010.01 | DO Separator Booster Pumps No.01 | Engine | 2026-01-13 | 39282 | - | 0.00 | 0 | 3rd Engineer | 13-Jan-2025 | No | Calendar
57 | MKR-IN-00058-702.010.02-2026-001 | Purifier Gear Pump, Visual Check - 1Y | 702.010.02 | DO Separator Booster Pumps No.02 | Engine | 2026-01-13 | 39282 | - | 0.00 | 0 | 3rd Engineer | 13-Jan-2025 | No | Calendar
58 | MKR-IN-00089-721.801.02-2026-001 | Electric Motor Megger Test - 1M | 721.801.02 | El. Motor, Main Sw Cooling Pumps No.02 | Engine | 2026-01-13 | 39282 | - | 0.00 | 0 | Electrican | 13-Dec-2025 | No | Calendar
59 | MKR-IN-00056-702.005.01-2026-001 | Purifier Parts, Visual Check - 1Y | 702.005.01 | FO Separators No.01 | Engine | 2026-01-13 | 39282 | - | 0.00 | 0 | 3rd Engineer | 13-Jan-2025 | No | Calendar
60 | MKR-IN-00056-702.005.02-2026-001 | Purifier Parts, Visual Check - 1Y | 702.005.02 | FO Separators No.02 | Engine | 2026-01-13 | 39282 | - | 0.00 | 0 | 3rd Engineer | 13-Jan-2025 | No | Calendar
61 | MKR-IN-00076-601.005.01-2026-001 | Main Engine – Connecting Rods, Crosshead & Guide Assemblies Inspection - 1M | 601.005.01 | ME Connecting Rods, Crosshead, Guides No.01 | Engine | 2026-01-13 | 39282 | - | 4020.00 | 0 | 2nd Engineer | 13-Dec-2025 | No | Calendar
62 | MKR-IN-00076-601.005.02-2026-001 | Main Engine – Connecting Rods, Crosshead & Guide Assemblies Inspection - 1M | 601.005.02 | ME Connecting Rods, Crosshead, Guides No.02 | Engine | 2026-01-13 | 39282 | - | 4020.00 | 0 | 2nd Engineer | 13-Dec-2025 | No | Calendar
63 | MKR-IN-00076-601.005.06-2026-001 | Main Engine – Connecting Rods, Crosshead & Guide Assemblies Inspection - 1M | 601.005.06 | ME Connecting Rods, Crosshead, Guides No.06 | Engine | 2026-01-13 | 39282 | - | 4020.00 | 0 | 2nd Engineer | 13-Dec-2025 | No | Calendar
64 | MKR-IN-00078-601.059-2026-001 | Main Engine – Exhaust Gas Manifolds & Pipes with Insulation Inspection - 1M | 601.059 | ME Exhaust Gas Manifolds/Pipes W/Insulation | Engine | 2026-01-13 | 39282 | - | 4020.00 | 0 | 2nd Engineer | 13-Dec-2025 | No | Calendar
65 | MKR-IN-00079-601.066.03-2026-001 | Main Engine – Indicator Valves & Indicators Inspection - 1M | 601.066.03 | ME Indicators No.03 | Engine | 2026-01-13 | 39282 | - | 4020.00 | 0 | 2nd Engineer | 13-Dec-2025 | No | Calendar
66 | MKR-IN-00079-601.066.06-2026-001 | Main Engine – Indicator Valves & Indicators Inspection - 1M | 601.066.06 | ME Indicators No.06 | Engine | 2026-01-13 | 39282 | - | 4020.00 | 0 | 2nd Engineer | 13-Dec-2025 | No | Calendar
67 | MKR-IN-00080-651.002.01-2026-001 | AE Cylinder Covers with Valves Inspection - 1M | 651.002.01 | AE1 Cylinder Covers W/Valves No.01 | Engine | 2026-01-14 | 38917 | - | 20.00 | 0 | 3rd Engineer | 14-Dec-2025 | No | Calendar
68 | MKR-IN-00080-651.002.02-2026-001 | AE Cylinder Covers with Valves Inspection - 1M | 651.002.02 | AE1 Cylinder Covers W/Valves No.02 | Engine | 2026-01-14 | 38917 | - | 20.00 | 0 | 3rd Engineer | 14-Dec-2025 | No | Calendar
69 | MKR-IN-00080-651.002.04-2026-001 | AE Cylinder Covers with Valves Inspection - 1M | 651.002.04 | AE1 Cylinder Covers W/Valves No.04 | Engine | 2026-01-14 | 38917 | - | 20.00 | 0 | 3rd Engineer | 14-Dec-2025 | No | Calendar
70 | MKR-IN-00085-651.003.02-2026-001 | AE Cylinder Liner Inspection - 1M | 651.003.02 | AE1 Cylinder Liners No.02 | Engine | 2026-01-14 | 38917 | - | 20.00 | 0 | 3rd Engineer | 14-Dec-2025 | No | Calendar
71 | MKR-IN-00085-651.003.04-2026-001 | AE Cylinder Liner Inspection - 1M | 651.003.04 | AE1 Cylinder Liners No.04 | Engine | 2026-01-14 | 38917 | - | 20.00 | 0 | 3rd Engineer | 14-Dec-2025 | No | Calendar
72 | MKR-IN-00080-652.002.01-2026-001 | AE Cylinder Covers with Valves Inspection - 1M | 652.002.01 | AE2 Cylinder Covers W/Valves No.01 | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | 3rd Engineer | 14-Dec-2025 | No | Calendar
73 | MKR-IN-00080-652.002.03-2026-001 | AE Cylinder Covers with Valves Inspection - 1M | 652.002.03 | AE2 Cylinder Covers W/Valves No.03 | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | 3rd Engineer | 14-Dec-2025 | No | Calendar
74 | MKR-IN-00085-652.003.01-2026-001 | AE Cylinder Liner Inspection - 1M | 652.003.01 | AE2 Cylinder Liners No.01 | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | 3rd Engineer | 14-Dec-2025 | No | Calendar
75 | MKR-IN-00085-652.003.04-2026-001 | AE Cylinder Liner Inspection - 1M | 652.003.04 | AE2 Cylinder Liners No.04 | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | 3rd Engineer | 14-Dec-2025 | No | Calendar
76 | MKR-IN-00080-653.002.02-2026-001 | AE Cylinder Covers with Valves Inspection - 1M | 653.002.02 | AE3 Cylinder Covers W/Valves No.02 | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | 3rd Engineer | 14-Dec-2025 | No | Calendar
77 | MKR-IN-00080-653.002.03-2026-001 | AE Cylinder Covers with Valves Inspection - 1M | 653.002.03 | AE3 Cylinder Covers W/Valves No.03 | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | 3rd Engineer | 14-Dec-2025 | No | Calendar
78 | MKR-IN-00080-653.002.05-2026-001 | AE Cylinder Covers with Valves Inspection - 1M | 653.002.05 | AE3 Cylinder Covers W/Valves No.05 | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | 3rd Engineer | 14-Dec-2025 | No | Calendar
79 | MKR-IN-00085-653.003.01-2026-001 | AE Cylinder Liner Inspection - 1M | 653.003.01 | AE3 Cylinder Liners No.01 | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | 3rd Engineer | 14-Dec-2025 | No | Calendar
80 | MKR-IN-00085-653.003.04-2026-001 | AE Cylinder Liner Inspection - 1M | 653.003.04 | AE3 Cylinder Liners No.04 | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | 3rd Engineer | 14-Dec-2025 | No | Calendar
81 | MKR-OV-00010-721.003.01-2026-001 | Pump, Overhaul - 48M/20000H | 721.003.01 | Aux. Sw Cooling Pumps No.01 | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | 2nd Engineer | 14-Jan-2022 | No | Calendar
82 | MKR-IN-00062-721.003.01-2026-001 | Pump Parts, Inspection - 12M/8000H | 721.003.01 | Aux. Sw Cooling Pumps No.01 | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | 2nd Engineer | 14-Jan-2025 | No | Calendar
83 | MKR-IN-00061-721.003.02-2026-001 | Pump General, Routine - 3M | 721.003.02 | Aux. Sw Cooling Pumps No.02 | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | 2nd Engineer | 14-Oct-2025 | No | Calendar
84 | MKR-IN-00072-285.001.05-2026-001 | Ballast Tanks Inspection - 1M | 285.001.05 | Ballast Tanks/SW Tanks No.05 | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | 2nd Engineer | 14-Dec-2025 | No | Calendar
85 | MKR-IN-00072-285.001.06-2026-001 | Ballast Tanks Inspection - 1M | 285.001.06 | Ballast Tanks/SW Tanks No.06 | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | 2nd Engineer | 14-Dec-2025 | No | Calendar
86 | MKR-IN-00072-285.001.07-2026-001 | Ballast Tanks Inspection - 1M | 285.001.07 | Ballast Tanks/SW Tanks No.07 | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | 2nd Engineer | 14-Dec-2025 | No | Calendar
87 | MKR-SE-00024-801.001-2026-001 | Ballast Pump Ball Bearing Grease, Renewal - 12M | 801.001 | Clean Ballast Pumps | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | Chief Engineer | 14-Jan-2025 | No | Calendar
88 | MKR-IN-00057-702.010.01-2026-001 | Purifier Gear Pump Safety Joint, Visual Check - 6M | 702.010.01 | DO Separator Booster Pumps No.01 | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | 3rd Engineer | 14-Jul-2025 | No | Calendar
89 | MKR-IN-00055-702.005.01-2026-001 | Purifier, Visual Check - 3M | 702.005.01 | FO Separators No.01 | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | 3rd Engineer | 14-Oct-2025 | No | Calendar
90 | MKR-IN-00059-712.013.01-2026-001 | Gear Pump, Routine - 3M | 712.013.01 | LO Separator Booster Pumps No.01 | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | 3rd Engineer | 14-Oct-2025 | No | Calendar
91 | MKR-OV-00009-712.013.02-2026-001 | Gear Pump, Overhaul - 48M/20000H | 712.013.02 | LO Separator Booster Pumps No.02 | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | 3rd Engineer | 14-Jan-2022 | No | Calendar
92 | MKR-IN-00060-712.013.02-2026-001 | Gear Pump Parts, Inspection - 12M/8000H | 712.013.02 | LO Separator Booster Pumps No.02 | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | 3rd Engineer | 14-Jan-2025 | No | Calendar
93 | MKR-OV-00008-712.011.02-2026-001 | Purifier, Overhaul - 6M | 712.011.02 | LO Separators No.02 | Engine | 2026-01-14 | 38917 | - | 1501.00 | 0 | 3rd Engineer | 14-Jul-2025 | No | Calendar
94 | MKR-OV-00010-721.001.01-2026-001 | Pump, Overhaul - 48M/20000H | 721.001.01 | Main Sw Cooling Pumps No.01 | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | 2nd Engineer | 14-Jan-2022 | No | Calendar
95 | MKR-IN-00061-721.001.02-2026-001 | Pump General, Routine - 3M | 721.001.02 | Main Sw Cooling Pumps No.02 | Engine | 2026-01-14 | 38917 | - | 0.00 | 0 | 2nd Engineer | 14-Oct-2025 | No | Calendar
96 | MKR-IN-00076-601.005.05-2026-001 | Main Engine – Connecting Rods, Crosshead & Guide Assemblies Inspection - 1M | 601.005.05 | ME Connecting Rods, Crosshead, Guides No.05 | Engine | 2026-01-14 | 38917 | - | 4020.00 | 0 | 2nd Engineer | 14-Dec-2025 | No | Calendar
97 | MKR-IN-00079-601.066.01-2026-001 | Main Engine – Indicator Valves & Indicators Inspection - 1M | 601.066.01 | ME Indicators No.01 | Engine | 2026-01-14 | 38917 | - | 4020.00 | 0 | 2nd Engineer | 14-Dec-2025 | No | Calendar
98 | MKR-IN-00079-601.066.05-2026-001 | Main Engine – Indicator Valves & Indicators Inspection - 1M | 601.066.05 | ME Indicators No.05 | Engine | 2026-01-14 | 38917 | - | 4020.00 | 0 | 2nd Engineer | 14-Dec-2025 | No | Calendar
99 | MKR-IN-00085-651.003.06-2026-002 | AE Cylinder Liner Inspection - 1M | 651.003.06 | AE1 Cylinder Liners No.06 | Engine | 2026-02-14 | 38886 | - | 20.00 | 0 | 3rd Engineer | 2026-01-14 | No | Calendar
100 | MKR-IN-00014-653.001-2026-001 | DG General, Visual Check - 1W | 653.001 | Aux. Diesel Generator Aggregates, Complete No.03 | Engine | 2026-01-16 | 38187 | - | 0.00 | 0 | 3rd Engineer | 09-Jan-2026 | No | Calendar
101 | MKR-SE-00021-702.005.01-2026-001 | Purifier Parts, Renewal/Replace - 2Y | 702.005.01 | FO Separators No.01 | Engine | 2026-01-16 | 38187 | - | 0.00 | 0 | 3rd Engineer | 16-Jan-2024 | No | Calendar
102 | MKR-SE-00021-702.005.02-2026-001 | Purifier Parts, Renewal/Replace - 2Y | 702.005.02 | FO Separators No.02 | Engine | 2026-01-16 | 38187 | - | 0.00 | 0 | 3rd Engineer | 16-Jan-2024 | No | Calendar
103 | MKR-IN-00054-712.011.01-2026-001 | Purifier, Routine - 1W | 712.011.01 | LO Separators No.01 | Engine | 2026-01-16 | 38187 | - | 0.00 | 0 | 3rd Engineer | 09-Jan-2026 | No | Calendar
104 | MKR-IN-00054-712.011.02-2026-001 | Purifier, Routine - 1W | 712.011.02 | LO Separators No.02 | Engine | 2026-01-16 | 38187 | - | 1501.00 | 0 | 3rd Engineer | 09-Jan-2026 | No | Calendar
105 | MKR-IN-00042-403.001-2026-001 | Steering Gear Oil, Routine - 1W | 403.001 | Steering Gears, Complete | Engine | 2026-01-16 | 38187 | - | 0.00 | 0 | 2nd Engineer | 09-Jan-2026 | No | Calendar
106 | MKR-IN-00080-651.002.05-2026-001 | AE Cylinder Covers with Valves Inspection - 1M | 651.002.05 | AE1 Cylinder Covers W/Valves No.05 | Engine | 2026-01-18 | 37456 | - | 20.00 | 0 | 3rd Engineer | 18-Dec-2025 | No | Calendar
107 | MKR-IN-00080-652.002.04-2026-001 | AE Cylinder Covers with Valves Inspection - 1M | 652.002.04 | AE2 Cylinder Covers W/Valves No.04 | Engine | 2026-01-18 | 37456 | - | 0.00 | 0 | 3rd Engineer | 18-Dec-2025 | No | Calendar
108 | MKR-IN-00085-652.003.06-2026-001 | AE Cylinder Liner Inspection - 1M | 652.003.06 | AE2 Cylinder Liners No.06 | Engine | 2026-01-18 | 37456 | - | 0.00 | 0 | 3rd Engineer | 18-Dec-2025 | No | Calendar
109 | MKR-IN-00085-653.003.03-2026-001 | AE Cylinder Liner Inspection - 1M | 653.003.03 | AE3 Cylinder Liners No.03 | Engine | 2026-01-18 | 37456 | - | 0.00 | 0 | 3rd Engineer | 18-Dec-2025 | No | Calendar
110 | MKR-IN-00072-285.001.03-2026-001 | Ballast Tanks Inspection - 1M | 285.001.03 | Ballast Tanks/SW Tanks No.03 | Engine | 2026-01-18 | 37456 | - | 0.00 | 0 | 2nd Engineer | 18-Dec-2025 | No | Calendar
111 | MKR-IN-00089-721.801.01-2026-001 | Electric Motor Megger Test - 1M | 721.801.01 | El. Motor, Main Sw Cooling Pumps No.01 | Engine | 2026-01-18 | 37456 | - | 0.00 | 0 | Electrican | 18-Dec-2025 | No | Calendar
112 | MKR-SE-00022-702.005.01-2026-001 | Purifier Multi Monitor Pressure Sensor, Renewal/Replace - 3Y | 702.005.01 | FO Separators No.01 | Engine | 2026-01-18 | 37456 | - | 0.00 | 0 | 3rd Engineer | 18-Jan-2023 | No | Calendar
113 | MKR-SE-00022-702.005.02-2026-001 | Purifier Multi Monitor Pressure Sensor, Renewal/Replace - 3Y | 702.005.02 | FO Separators No.02 | Engine | 2026-01-18 | 37456 | - | 0.00 | 0 | 3rd Engineer | 18-Jan-2023 | No | Calendar
114 | MKR-SE-00022-712.011.01-2026-001 | Purifier Multi Monitor Pressure Sensor, Renewal/Replace - 3Y | 712.011.01 | LO Separators No.01 | Engine | 2026-01-18 | 37456 | - | 0.00 | 0 | 3rd Engineer | 18-Jan-2023 | No | Calendar
115 | MKR-IN-00076-601.005.04-2026-001 | Main Engine – Connecting Rods, Crosshead & Guide Assemblies Inspection - 1M | 601.005.04 | ME Connecting Rods, Crosshead, Guides No.04 | Engine | 2026-01-18 | 37456 | - | 4020.00 | 0 | 2nd Engineer | 18-Dec-2025 | No | Calendar
116 | MKR-IN-00079-601.066.02-2026-001 | Main Engine – Indicator Valves & Indicators Inspection - 1M | 601.066.02 | ME Indicators No.02 | Engine | 2026-01-18 | 37456 | - | 4020.00 | 0 | 2nd Engineer | 18-Dec-2025 | No | Calendar
117 | MKR-SE-00020-601.026.01-2026-001 | ME Valves, Renewal/Replace - 5Y | 601.026.01 | ME Hp Fuel Pumps No.01 | Engine | 2026-01-19 | 37091 | - | 4020.00 | 0 | 2nd Engineer | 19-Jan-2021 | No | Calendar
118 | MKR-SE-00020-601.026.02-2026-001 | ME Valves, Renewal/Replace - 5Y | 601.026.02 | ME Hp Fuel Pumps No.02 | Engine | 2026-01-19 | 37091 | - | 4020.00 | 0 | 2nd Engineer | 19-Jan-2021 | No | Calendar
119 | MKR-SE-00014-403.001-2026-001 | Steering Gear Rotor Seal & Gland Seal, Renewal/Replace - 5Y | 403.001 | Steering Gears, Complete | Engine | 2026-01-19 | 37091 | - | 0.00 | 0 | 2nd Engineer | 19-Jan-2021 | No | Calendar
120 | MKR-IN-00052-554.005.01-2026-001 | Provision Ref. Condensers Pressure Switch, Visual Check - 1Y | 554.005.01 | Condensers No.01 | Engine | 2026-01-20 | 36726 | - | 0.00 | 0 | 2nd Engineer | 20-Jan-2025 | No | Calendar
121 | MKR-IN-00052-554.005.02-2026-001 | Provision Ref. Condensers Pressure Switch, Visual Check - 1Y | 554.005.02 | Condensers No.02 | Engine | 2026-01-20 | 36726 | - | 0.00 | 0 | 2nd Engineer | 20-Jan-2025 | No | Calendar
122 | MKR-IN-00068-601.053-2026-001 | ME Turbocharger Major Parts, Visual Check - 1Y | 601.053 | ME Turbochargers | Engine | 2026-01-20 | 36726 | - | 2015.00 | 0 | 2nd Engineer | 20-Jan-2025 | No | Calendar
123 | MKR-IN-00043-403.001-2026-001 | Steering Gear Actuator Stuffing Gland, Inspection - 1Y | 403.001 | Steering Gears, Complete | Engine | 2026-01-20 | 36726 | - | 0.00 | 0 | 2nd Engineer | 20-Jan-2025 | No | Calendar
124 | MKR-IN-00014-651.001-2026-001 | DG General, Visual Check - 1W | 651.001 | Aux. Diesel Generator Aggregates, Complete No.01 | Engine | 2026-01-21 | 36360 | - | 20.00 | 0 | 3rd Engineer | 14-Jan-2026 | No | Calendar
125 | MKR-OV-00010-721.003.02-2026-001 | Pump, Overhaul - 48M/20000H | 721.003.02 | Aux. Sw Cooling Pumps No.02 | Engine | 2026-01-21 | 36360 | - | 0.00 | 0 | 2nd Engineer | 21-Jan-2022 | No | Calendar
126 | MKR-OV-00009-712.013.01-2026-001 | Gear Pump, Overhaul - 48M/20000H | 712.013.01 | LO Separator Booster Pumps No.01 | Engine | 2026-01-21 | 36360 | - | 0.00 | 0 | 3rd Engineer | 21-Jan-2022 | No | Calendar
127 | MKR-OV-00010-721.001.02-2026-001 | Pump, Overhaul - 48M/20000H | 721.001.02 | Main Sw Cooling Pumps No.02 | Engine | 2026-01-21 | 36360 | - | 0.00 | 0 | 2nd Engineer | 21-Jan-2022 | No | Calendar
128 | MKR-IN-00046-554.001-2026-001 | Provision Refrigeration Unit, Routine - 1W | 554.001 | Provision Cooling Compressor Aggregates | Engine | 2026-01-21 | 36360 | - | 240.00 | 0 | 2nd Engineer | 14-Jan-2026 | No | Calendar
129 | MKR-IN-00074-601.001-2026-002 | Main Engine General Inspection - 1M | 601.001 | Main Diesel Engine, Compl. | Engine | 2026-02-21 | 36329 | - | 4020.00 | 0 | 2nd Engineer | 2026-01-21 | No | Calendar
130 | MKR-IN-00014-652.001-2026-001 | DG General, Visual Check - 1W | 652.001 | Aux. Diesel Generator Aggregates, Complete No.02 | Engine | 2025-12-21 | 36027 | - | 0.00 | 0 | 3rd Engineer | 14-Dec-2025 | No | Calendar
131 | MKR-IN-00062-721.003.02-2026-001 | Pump Parts, Inspection - 12M/8000H | 721.003.02 | Aux. Sw Cooling Pumps No.02 | Engine | 2026-01-22 | 35995 | - | 0.00 | 0 | 2nd Engineer | 22-Jan-2025 | No | Calendar
132 | MKR-IN-00060-712.013.01-2026-001 | Gear Pump Parts, Inspection - 12M/8000H | 712.013.01 | LO Separator Booster Pumps No.01 | Engine | 2026-01-22 | 35995 | - | 0.00 | 0 | 3rd Engineer | 22-Jan-2025 | No | Calendar
133 | MKR-IN-00062-721.001.02-2026-001 | Pump Parts, Inspection - 12M/8000H | 721.001.02 | Main Sw Cooling Pumps No.02 | Engine | 2026-01-22 | 35995 | - | 0.00 | 0 | 2nd Engineer | 22-Jan-2025 | No | Calendar
134 | MKR-IN-00061-721.003.01-2026-001 | Pump General, Routine - 3M | 721.003.01 | Aux. Sw Cooling Pumps No.01 | Engine | 2026-01-25 | 34899 | - | 0.00 | 0 | 2nd Engineer | 25-Oct-2025 | No | Calendar
135 | MKR-IN-00059-712.013.02-2026-001 | Gear Pump, Routine - 3M | 712.013.02 | LO Separator Booster Pumps No.02 | Engine | 2026-01-25 | 34899 | - | 0.00 | 0 | 3rd Engineer | 25-Oct-2025 | No | Calendar
136 | MKR-IN-00055-712.011.01-2026-001 | Purifier, Visual Check - 3M | 712.011.01 | LO Separators No.01 | Engine | 2026-01-25 | 34899 | - | 0.00 | 0 | 3rd Engineer | 25-Oct-2025 | No | Calendar
137 | MKR-IN-00047-554.001-2026-001 | Provision Refrigeration Unit, Visual Check - 3M | 554.001 | Provision Cooling Compressor Aggregates | Engine | 2026-01-25 | 34899 | - | 240.00 | 0 | 2nd Engineer | 25-Oct-2025 | No | Calendar
138 | MKR-IN-00054-702.005.01-2026-002 | Purifier, Routine - 1W | 702.005.01 | FO Separators No.01 | Engine | 2026-01-28 | 33804 | - | 0.00 | 0 | 3rd Engineer | 2026-01-21 | No | Calendar
139 | MKR-IN-00085-651.003.01-2026-002 | AE Cylinder Liner Inspection - 1M | 651.003.01 | AE1 Cylinder Liners No.01 | Engine | 2026-01-31 | 32708 | - | 20.00 | 0 | 3rd Engineer | 2025-12-31 | No | Calendar
140 | MKR-IN-00063-601.004.01-2026-001 | ME Piston And Rings, Inspection - 500H | 601.004.01 | ME Pistons, Piston Rods No.01 | Engine | - | 0 | 500 | 4020.00 | 3520 | 2nd Engineer | - | No | RH
141 | MKR-IN-00063-601.004.02-2026-001 | ME Piston And Rings, Inspection - 500H | 601.004.02 | ME Pistons, Piston Rods No.02 | Engine | - | 0 | 500 | 4020.00 | 3520 | 2nd Engineer | - | No | RH
142 | MKR-IN-00063-601.004.04-2026-001 | ME Piston And Rings, Inspection - 500H | 601.004.04 | ME Pistons, Piston Rods No.04 | Engine | - | 0 | 500 | 4020.00 | 3520 | 2nd Engineer | - | No | RH
143 | MKR-IN-00063-601.004.06-2026-001 | ME Piston And Rings, Inspection - 500H | 601.004.06 | ME Pistons, Piston Rods No.06 | Engine | - | 0 | 500 | 4020.00 | 3520 | 2nd Engineer | - | No | RH
144 | MKR-IN-00066-601.053-2026-001 | ME Turbocharger Turbine, Cleaning - 500H | 601.053 | ME Turbochargers | Engine | - | 0 | 500 | 2015.00 | 1515 | 2nd Engineer | - | No | RH
SUMMARY:
Total Overdue Jobs: | 144
Critical Equipment Overdue: | 9
Average Days Overdue: | 37562.8
Longest Overdue: | 43300 days
Calendar Overdue: | 139
RH Overdue: | 5
ACTION REQUIRED: All overdue jobs must be completed or officially postponed with Master's approval