## Dashboard
SAIL PMS ¦ PROJECT PROGRESS | [5 empty] | Activity status | Count | Critical category | Received | Not received
[6 empty] | Completed |  | Components
Stakeholder view / SAIL uploads data received from WK. Client-side validation, reviews and remaining inputs/actions are pending with WK. | [5 empty] | Open |  | Spares
[6 empty] | Not Applicable |  | Jobs
| Reporting period | 2026-09-29 | Last updated | 2026-09-29 |  | Not assessed
| Responsible person | Jeevan | Reporting to / audience | Wah Kwong Team
| SAIL TEAM / DELIVERY |  | CLIENT SIDE / ACTIONS TO CONFIRM |  | CLIENT-SIDE ACTIVITY STATUS
| Data received from WK (weighted) | 30 / 30 / 30 / 10 | Open items (confirmed)
| Data loaded by SAIL (weighted) | 30 / 30 / 30 / 10 | Activities without status
| No Of Components Missing jobs | Components affected | Completed activities
| No Of Components Missing spares | Components affected | Only confirmed statuses count as open or complete. Unassessed activities are listed separately; they are not assumed pending.
| Critical items received | Received / estimated baseline
| WOs generated till now | Cumulative count | CLIENT STATUS / REMARKS |  | CRITICAL ITEMS / RECEIPT
SAIL Team scope: upload data received from WK. WK Team owns source-data verification, required inputs, reviews and decisions.
| RH machinery updated | Vessel updated / created
WO status counts can overlap. Repeated cycles can produce several WOs per job; no jobs-based percentage.
REPORTING NOTES / EDITABLE
| Key completed points | Available Components, Jobs and Maker list data uploaded to SAIL PMS. WK verification remains pending.
| Pending points / next actions | WK Team to provide spare data, confirm the Stores baseline, and complete the listed reviews and PMS decisions.
| Major risks / gaps | Category baselines are rough estimates retained for weighted calculations; WK confirmation is needed before treating them as final.
| Other remarks | SAIL responsibility is limited to uploading received data. All other inputs, verification and decisions remain with WK.
Weighted data KPIs: Components 30%, Jobs 30%, Spares 30%, Stores 10%. Zero-baseline categories are excluded and active weights normalized; Maker list excluded.
WORK ORDERS / RH MACHINERY SNAPSHOT
| Due |  | Overdue
| Active |  | Pending approval |  | Critical chart compares received and pending WK quantities. SAIL loaded counts are shown in the tracker.
| Completed |  | RH machinery created
| Vessel RH details updated |  | RH not updated

## Update Tracker
SAIL PMS ¦ UPDATE TRACKER
Yellow = editable input • Pale blue = calculated • Blank = not confirmed; enter 0 only when confirmed. All quantities are whole, nonnegative counts.
01 / SAIL TEAM — DATA UPLOAD STATUS
Data category | Received from WK | Loaded in SAIL | Pending from WK (est.) | Received % | Loaded % | SAIL upload status | SAIL upload owner | Last updated | Target date | Remarks / evidence |  | Hidden estimated denominator — weighted data KPI
Components | 1500 | 1500 |  |  |  | Completed | SAIL Team | 2026-09-29 | 2026-09-29 | Data Loaded As per the details shared by Wah Kwong, Data verification has to be done by Wah Kwong team |  | 1500
Jobs | 2000 | 2000 |  |  |  | Completed | SAIL Team | 2026-09-29 | 2026-09-29 | Data Loaded As per the details shared by Wah Kwong, Data verification has to be done by Wah Kwong team |  | 2000
Spares | 0 | 0 |  |  |  | Pending Wah Kwong Input | SAIL Team | 2026-09-29 | 2026-09-29 | Awaiting for the data from Wah Kwong team |  | 18000
Stores | 0 | 0 |  |  |  | Pending Wah Kwong Input | SAIL Team | 2026-09-29 | 2026-09-29 | Awaiting for the data from Wah Kwong team |  | 0
Maker list | 50 | 50 |  |  |  | Completed | SAIL Team | 2026-09-29 | 2026-09-29 | Data Loaded As per the details shared by Wah Kwong, Data verification has to be done by Wah Kwong team |  | 50
Weighted data percentages use the existing rough-estimate baselines retained in hidden calculation cells. Zero-baseline categories are excluded and the remaining weights are normalized; Maker list is excluded.
02 / CLIENT-SIDE DATA GAPS — JOBS & SPARES FOR COMPONENTS
Gap | No. of components | Affected component IDs / names |  |  |  | Status | Owner | Target date | Last updated | Next action / remarks
No Of Components Missing jobs | 200 |  |  |  |  | Pending Wah Kwong Input | Wah Kwong Team |  |  | Dates needs to updated by Wah Kwong Team
No Of Components Missing spares | 1500 |  |  |  |  | Pending Wah Kwong Input | Wah Kwong Team |  |  | Dates needs to updated by Wah Kwong Team
List affected components by ID or name. A component missing both jobs and spares may appear in both rows; these counts must not be added together.
03 / CLIENT-SIDE — CRITICAL DATA RECEIPT, SAIL LOAD & WK VERIFICATION
Critical category | Received from WK | Loaded in SAIL | Pending from WK (est.) | Pending for SAIL upload | Received % | Loaded % | WK verification status | WK owner | Last updated | Target date | Remarks / evidence |  | Hidden estimated denominator — critical items
Critical Components | 50 | [5 empty] | Pending Review | Wah Kwong / WK Team |  |  | Dates needs to updated by Wah Kwong Team |  | 50
Critical Spares | 0 | [5 empty] | Pending Wah Kwong Input | Wah Kwong / WK Team |  |  | Dates needs to updated by Wah Kwong Team |  | 50
Critical Jobs | 50 | [5 empty] | Pending Review | Wah Kwong / WK Team |  |  | Dates needs to updated by Wah Kwong Team |  | 50
Critical receipt and SAIL loading are tracked separately. Loaded counts are blank until confirmed; WK verification and outstanding critical spare data remain pending.
04 / CLIENT-SIDE INPUTS, REVIEWS & DECISIONS — PENDING FROM WK
Activity / requirement | Total required | Done / supplied | Remaining | Status | Priority | Owner | Target date | Completed date | Last updated | Next action / remarks
Equipment register / source data |  |  |  | Pending Wah Kwong Input |  | Wah Kwong / WK Team |  |  |  | Pending input, review or decision from WK Team.
Maker manuals collection |  |  |  | Pending Wah Kwong Input |  | Wah Kwong / WK Team |  |  |  | Pending input, review or decision from WK Team.
Supporting documentation |  |  |  | Pending Wah Kwong Input |  | Wah Kwong / WK Team |  |  |  | Pending input, review or decision from WK Team.
Task procedures / instructions |  |  |  | Pending Wah Kwong Input |  | Wah Kwong / WK Team |  |  |  | Pending input, review or decision from WK Team.
PMS interval verification |  |  |  | Pending Wah Kwong Input |  | Wah Kwong / WK Team |  |  |  | Pending input, review or decision from WK Team.
Spare parts source data |  |  |  | Pending Wah Kwong Input |  | Wah Kwong / WK Team |  |  |  | Pending input, review or decision from WK Team.
Component-job-spare mapping inputs |  |  |  | Pending Wah Kwong Input |  | Wah Kwong / WK Team |  |  |  | Pending input, review or decision from WK Team.
Criticality / risk review |  |  |  | Pending Wah Kwong Input |  | Wah Kwong / WK Team |  |  |  | Pending input, review or decision from WK Team.
Class / statutory task review |  |  |  | Pending Wah Kwong Input |  | Wah Kwong / WK Team |  |  |  | Pending input, review or decision from WK Team.
SMS / final verification |  |  |  | Pending Wah Kwong Input |  | Wah Kwong / WK Team |  |  |  | Pending input, review or decision from WK Team.
Data quality / missing-field clarifications |  |  |  | Pending Wah Kwong Input |  | Wah Kwong / WK Team |  |  |  | Pending input, review or decision from WK Team.
PMS changes: client decisions |  |  |  | Pending Wah Kwong Input |  | Wah Kwong / WK Team |  |  |  | Pending input, review or decision from WK Team.
Client activities are a checklist, not assumed open or assigned. Leave unconfirmed owners, quantities, dates and statuses blank.
05 / SAIL PMS SYSTEM OUTPUT — AUTO-GENERATED WORK ORDERS
Measure | No. of WOs | Status | Owner | Last updated | Remarks / evidence
Generated till now | 8000 | In Progress | Sail System | 2026-09-29 | The WO Will be auto Generated based on the Maker Manual Interval
Due | 200 | In Progress | Sail System | 2026-09-29 | The WO Will be auto Generated based on the Maker Manual Interval
Overdue | 500 | In Progress | Sail System | 2026-09-29 | The WO Will be auto Generated based on the Maker Manual Interval
Active | 200 | In Progress | Sail System | 2026-09-29 | The WO Will be auto Generated based on the Maker Manual Interval
Pending approval | 200 | In Progress | Sail System | 2026-09-29 | The WO Will be auto Generated based on the Maker Manual Interval
Completed | 6500 | Completed | Sail System | 2026-09-29 | The WO Will be auto Generated based on the Maker Manual Interval
Work orders are system-generated from configured intervals. Status counts can overlap; one job can generate multiple WOs across cycles.
06 / CLIENT / VESSEL ACTION — RH DETAILS PENDING
Machinery scope | RH machinery created | Vessel RH details updated | Not updated | Updated % | Status | Owner | Last updated | Target date | Remarks / evidence
RH Machinery | 42 | 40 |  |  | Pending Wah Kwong Action | Wah Kwong / WK Team |  |  | Vessel RH details remain pending for 2 components.
Created = RH machinery records in scope. Vessel updated = records for which the vessel has entered RH details. Not updated and Updated % calculate only when counts are confirmed.
UPDATE GUIDE / YELLOW = EDITABLE • PALE BLUE = CALCULATED • BLANK = UNKNOWN • 0 = CONFIRMED NONE
Set reporting details and short commentary on Dashboard. Confirm numbers with source owners before sharing; this workbook is not connected to live SAIL PMS data.
Note on M6: Existing estimated category baselines retained only for percentage calculations. Not displayed or printed in the stakeholder tracker.
Note on M7: Existing baseline retained for the weighted KPI; revise only when the scope is confirmed by WK.
Note on M8: Existing baseline retained for the weighted KPI; revise only when the scope is confirmed by WK.
Note on M9: Existing baseline retained for the weighted KPI; revise only when the scope is confirmed by WK.
Note on M10: Existing baseline retained for the weighted KPI; revise only when the scope is confirmed by WK.
Note on M11: Existing baseline retained for the weighted KPI; revise only when the scope is confirmed by WK.
Note on N21: Existing estimated critical-item baselines retained only for the receipt KPI and chart; not displayed or printed.
Note on N22: Existing baseline retained for critical receipt calculations; confirm with WK before treating as final.
Note on N23: Existing baseline retained for critical receipt calculations; confirm with WK before treating as final.
Note on N24: Existing baseline retained for critical receipt calculations; confirm with WK before treating as final.