## Dashboard
SAIL PMS ¦ IMPLEMENTATION PROGRESS | [5 empty] | WK activity status | Count | Critical category | Received | Not received
[6 empty] | Yes |  | Components
SAIL uploads data received from WK; remaining inputs and verification are with the Wah Kwong / WK Team. | [5 empty] | In Progress |  | Spares
[6 empty] | N |  | Jobs
| Reporting period | 2026-09-29 | Last updated | 2026-09-29 |  | Not assessed
| Responsible person | Jeevan | Reporting to / audience | Wah Kwong Team
| SAIL TEAM / DELIVERY |  | WK TEAM / ACTIONS TO CONFIRM |  | WK ACTIVITY STATUS
| Data received from WK (weighted) | 30 / 30 / 30 / 10 | Weighted progress
| Data loaded by SAIL (weighted) | 30 / 30 / 30 / 10 | Completed (Yes)
| Components missing jobs | Components affected | Open / incomplete
| Components missing spares | Components affected | Not assessed
| Critical data received | Received / estimated baseline | Score: Yes = 100% of weight; In Progress = 50%; N = 0%. Blank means not assessed.
| WOs generated till now | Cumulative count | CLIENT STATUS / REMARKS |  | CRITICAL ITEMS / RECEIPT
SAIL Team scope: upload data received from WK. WK Team owns source-data verification, required inputs, reviews and decisions.
| RH machinery updated | Vessel updated / created
WO status counts can overlap. Repeated cycles can produce several WOs per job; no jobs-based percentage.
REPORTING NOTES / EDITABLE
| Key completed points | Available Components, Jobs and Maker list data uploaded to SAIL PMS. WK verification remains pending.
| Pending points / next actions | WK Team to provide spare data, confirm the Stores baseline, and complete the listed reviews and PMS decisions.
| Major risks / gaps | Category baselines are rough estimates retained for weighted calculations; WK confirmation is needed before treating them as final.
| Other remarks | SAIL responsibility is limited to uploading received data. All other inputs, verification and decisions remain with WK.
Weighted data KPIs: Components 30%, Jobs 30%, Spares 30%, Stores 10%. Zero-baseline categories are excluded and active weights normalized; Maker list excluded.
WORK ORDERS / RH MACHINERY SNAPSHOT
| Due |  | Overdue
| Active |  | Pending approval |  | Critical chart compares received and pending WK quantities. SAIL loaded counts are shown in the tracker.
| Completed |  | RH machinery created
| Vessel RH details updated |  | RH not updated

## Update Tracker
SAIL PMS ¦ UPDATE TRACKER
Enter updates in yellow cells. Blue cells calculate automatically. Blank means unconfirmed; enter 0 only when confirmed.
Quick update: record quantities received from WK and quantities loaded in SAIL separately; use the dropdowns for statuses.
01 /DATA UPLOAD
Category | Received from WK | Loaded in SAIL | Pending WK* | Received % | Loaded % | Data Loading status | Updated | Target | Notes |  | Estimated baseline (hidden)
Components | 1500 | 1500 |  |  |  | Completed | 2026-09-29 | 2026-09-29 | Data Verification Pending from WK |  | 1500
Jobs | 2000 | 2000 |  |  |  | Completed | 2026-09-29 | 2026-09-29 | Data Verification Pending from WK |  | 2000
Spares | 0 | 0 |  |  |  | Pending Wah Kwong Input | 2026-09-29 | 2026-09-29 | Awaiting for the data from Wah Kwong team |  | 18000
Stores | 0 | 0 |  |  |  | Pending Wah Kwong Input | 2026-09-29 | 2026-09-29 | Awaiting for the data from Wah Kwong team |  | 0
Maker list | 50 | 50 |  |  |  | Completed | 2026-09-29 | 2026-09-29 | Data Verification Pending from WK |  | 50
Progress uses hidden rough-estimate baselines. Zero-baseline categories are excluded; Maker list is not weighted.
02 / DATA GAPS — JOBS & SPARES FOR COMPONENTS
Gap | Components | Component IDs / names |  |  |  | Status | Target | Updated | Next step / notes
Components missing jobs | 200 |  |  |  |  | Pending Wah Kwong Input |  |  | Dates needs to updated by Wah Kwong Team
Components missing spares | 1500 |  |  |  |  | Pending Wah Kwong Input |  |  | Dates needs to updated by Wah Kwong Team
List affected components by ID or name. A component with both gaps can appear in both rows, so do not add the counts.
03 / CRITICAL DATA — RECEIPT, SAIL LOADING & WK CHECK
Critical item | Received from WK | Loaded in SAIL | Pending WK* | Pending SAIL upload | Received % | Loaded % | WK status | Updated | Target | Notes | Estimated critical baseline (hidden)
Critical Components | 50 | 50 |  |  |  |  | Pending Review |  |  | Dates needs to updated by Wah Kwong Team | 50
Critical Spares | 0 | [5 empty] | Pending Wah Kwong Input |  |  | Dates needs to updated by Wah Kwong Team | 50
Critical Jobs | 50 | 50 |  |  |  |  | Pending Review |  |  | Dates needs to updated by Wah Kwong Team | 50
Track received and loaded separately. Leave unconfirmed quantities blank; hidden estimates support progress calculations only.
04 / WK TEAM INPUTS, REVIEWS & DECISIONS
Work Element | Description | Weight % | WK Completion | Score | Priority | Target | Completed | Updated | Notes / next action
Equipment Register Creation | All equipment listed | 20% | Yes |  | High |  |  |  | Pending input, review or decision from WK Team.
Maker Manuals Collection | OEM manuals uploaded | 15% | N | [5 empty] | Pending input, review or decision from WK Team.
PMS Job Creation | Maintenance tasks built | 25% | Yes
Interval Verification | Intervals confirmed | 10% | N | [5 empty] | Pending input, review or decision from WK Team.
Spare Parts Mapping | Parts linked | 10% | N | [5 empty] | Pending input, review or decision from WK Team.
Risk/Criticality Review | Criticality completed | 5% | N | [5 empty] | Pending input, review or decision from WK Team.
Class/Statutory Tasks | Compliance tasks added | 10% | N | [5 empty] | Pending input, review or decision from WK Team.
SMS Review | Final verification | 5% | N | [5 empty] | Pending input, review or decision from WK Team.
Supporting documentation | Supporting records and documentation collected | [7 empty] | Pending input, review or decision from WK Team.
Task procedures / instructions | Task procedures and operating instructions | [7 empty] | Pending input, review or decision from WK Team.
Spare parts source data | Spare-parts reference data received | [7 empty] | Pending input, review or decision from WK Team.
Data quality / missing-field clarifications | Resolve unclear or missing source data | [7 empty] | Pending input, review or decision from WK Team.
PMS changes: WK decisions | WK decisions on requested PMS changes | [7 empty] | Pending input, review or decision from WK Team.
WK team: choose Yes, In Progress or N. Scores calculate from the assigned weights; blank status means not assessed. Unweighted review lines are outside the 100% total.
05 / WORK ORDER SUMMARY — SAIL PMS
Measure | WO count | Status | Updated | Notes
Generated till now | 8000 | In Progress | 2026-09-29 | The WO Will be auto Generated based on the Maker Manual Interval
Due | 200 | In Progress | 2026-09-29 | The WO Will be auto Generated based on the Maker Manual Interval
Overdue | 500 | In Progress | 2026-09-29 | The WO Will be auto Generated based on the Maker Manual Interval
Active | 200 | In Progress | 2026-09-29 | The WO Will be auto Generated based on the Maker Manual Interval
Pending approval | 200 | In Progress | 2026-09-29 | The WO Will be auto Generated based on the Maker Manual Interval
Completed | 6500 | Completed | 2026-09-29 | The WO Will be auto Generated based on the Maker Manual Interval
Counts may overlap: one job can generate multiple work orders over several cycles.
06 / VESSEL ACTION — RUNNING-HOURS DETAILS
Machinery scope | RH machinery created | Vessel RH details updated | RH details pending | Updated % | Status | Updated | Target | Notes
RH Machinery | 42 | 40 |  |  | Pending Wah Kwong Action |  |  | Vessel RH details remain pending for 2 components.
Created = RH machinery in scope. Updated = records with vessel-entered hours. Pending and percentage calculate from confirmed counts.
Set reporting details on Dashboard. Confirm quantities with source owners before sharing; this workbook is not connected to live SAIL PMS data.
Note on AA6: Hidden rough-estimate denominators used by the weighted progress formulas. Update only when the baseline is confirmed.
Note on M21: Existing estimated critical-item baselines retained only for the receipt KPI and chart; not displayed or printed.
Note on AA21: Hidden rough-estimate denominators used by the critical-item formulas. Update only when the baseline is confirmed.
Note on M22: Existing baseline retained for critical receipt calculations; confirm with WK before treating as final.
Note on M23: Existing baseline retained for critical receipt calculations; confirm with WK before treating as final.
Note on M24: Existing baseline retained for critical receipt calculations; confirm with WK before treating as final.