## Dashboard
SAIL PMS ¦ IMPLEMENTATION PROGRESS - GAS MIA | [5 empty] | WK activity status | Count | Critical category | Received | Not received
[6 empty] | Completed |  | Components
SAIL uploads data received from WK; remaining inputs and verification are with the Wah Kwong / WK Team. | [5 empty] | In Progress |  | Spares
[6 empty] | Open |  | Jobs
| Reporting period | 2026-09-29 | Last updated | 2026-09-29 |  | Not assessed
| Responsible person | Sail Team | Reporting to / audience | Wah Kwong Team
| SAIL TEAM / DELIVERY |  | WK TEAM / ACTIONS TO CONFIRM |  | WK ACTIVITY STATUS
| Data received from WK (weighted) | 30 / 30 / 30 / 10 | Weighted progress
| Data loaded by SAIL (weighted) | 30 / 30 / 30 / 10 | Completed
| Components missing jobs | Components affected | Open / incomplete
| Components missing spares | Components affected | Not assessed
| Critical data received | Received / estimated baseline | Score: Completed = 100% of weight; In Progress = 50%; Open = 0%. Blank means not assessed.
Data KPI weights: Components 30% ¦ Jobs 30% ¦ Spares 30% ¦ Stores 10%
| WOs generated till now | Cumulative count | STATUS / REMARKS |  | CRITICAL ITEMS / RECEIPT
SAIL Team scope: upload data received from WK. WK Team owns source-data verification, required inputs, reviews and decisions.
| RH machinery updated | Vessel updated / created
WO status counts can overlap. Repeated cycles can produce several WOs per job; no jobs-based percentage.
REPORTING NOTES / EDITABLE
Key completed points
Pending points / next actions
Major risks / gaps
| Other remarks | WK team is responsible for updating activity status, target/completion dates and notes as work progresses.
30/30/30/10 are the weighted data KPI shares: Components 30%, Jobs 30%, Spares 30%, Stores 10%. Maker list is excluded; active weights are normalized.
WORK ORDERS / RH MACHINERY SNAPSHOT
| Due |  | Overdue
| Active |  | Pending approval |  | Critical chart compares received and pending WK quantities. SAIL loaded counts are shown in the tracker.
| Completed |  | RH machinery created
| Vessel RH details updated |  | RH not updated

## Update Tracker
SAIL PMS ¦ UPDATE TRACKER
Enter updates in yellow cells. Blue cells calculate automatically. Blank means unconfirmed; enter 0 only when confirmed.
Quick update: record quantities received from WK and quantities loaded in SAIL separately; use the dropdowns for statuses.
01 /DATA UPLOAD
Category | Received from WK | Loaded in SAIL | Pending WK* | Received % | Loaded % | Data Loading status | Updated | Target | Notes |  | Estimated baseline (hidden)
Components | 1661 | 1661 |  |  |  | Completed |  |  | The data received from WK has been successfully loaded into SAIL PMS. |  | 1661
Jobs | 2165 | 2165 |  |  |  | Completed |  |  | The data received from WK has been successfully loaded into SAIL PMS. |  | 2165
Spares | 114 | 114 |  |  |  | Pending Wah Kwong Input |  |  | Awaiting the remaining spare data from the WK team. |  | 18000
Stores | 0 | 0 |  |  |  | Pending Wah Kwong Input |  |  | Awaiting the remaining Stores data from the WK team. |  | 0
Maker list | 14 | 14 |  |  |  | Completed |  |  | The data received from WK has been successfully loaded into SAIL PMS. |  | 14
Progress uses hidden rough-estimate baselines. Zero-baseline categories are excluded; Maker list is not weighted.
02 / DATA GAPS — JOBS & SPARES FOR COMPONENTS
Gap | Components | Component IDs / names |  |  |  | Status | Target | Updated | Next step / notes
Components missing jobs | 406 |  |  |  |  | Pending Wah Kwong Input |  |  | The WK team needs to share the data for the missing jobs
Components missing spares | 1503 |  |  |  |  | Pending Wah Kwong Input |  |  | The WK team needs to share the data for the missing Spares
List affected components by ID or name. A component with both gaps can appear in both rows, so do not add the counts.
03 / CRITICAL DATA — RECEIPT, SAIL LOADING & WK CHECK
Critical item | Received from WK | Loaded in SAIL | Pending WK* | Pending SAIL upload | Received % | Loaded % | WK status | Updated | Target | Notes | Estimated critical baseline (hidden)
Critical Components | 36 | 36 |  |  |  |  | Completed |  |  | Criticality marking has been completed by the WK team and populated in the SAIL system. | 36
Critical Spares | 29 | 29 |  |  |  |  | Completed |  |  | Criticality marking has been completed by the WK team and populated in the SAIL system. | 29
Critical Jobs | 111 | 111 |  |  |  |  | Completed |  |  | Criticality marking has been completed by the WK team and populated in the SAIL system. | 111
Track received and loaded separately. Leave unconfirmed quantities blank; hidden estimates support progress calculations only.
04 / WK TEAM INPUTS, REVIEWS & DECISIONS
Work Element | Description | Weight % | Status | Score | Priority | Target | Completed | Updated | Notes / next action
Equipment Register Creation | All equipment listed | 20% | Completed |  | High |  |  |  | The status needs to be updated by the WK team based on the task progress.
Maker Manuals Collection | OEM manuals uploaded | 15% | In Progress |  | High |  |  |  | The status needs to be updated by the WK team based on the task progress.
PMS Job Creation | Maintenance tasks built | 25% | Completed |  | High |  |  |  | The status needs to be updated by the WK team based on the task progress.
Interval Verification | Intervals confirmed | 10% | In Progress |  | High |  |  |  | The status needs to be updated by the WK team based on the task progress.
Spare Parts Mapping | Parts linked | 10% | In Progress |  | High |  |  |  | The status needs to be updated by the WK team based on the task progress.
Risk/Criticality Review | Criticality completed | 5% | Completed |  | High |  |  |  | The status needs to be updated by the WK team based on the task progress.
Class/Statutory Tasks | Compliance tasks added | 10% | In Progress |  | High |  |  |  | The status needs to be updated by the WK team based on the task progress.
SMS Review | Final verification | 5% | In Progress |  | High |  |  |  | The status needs to be updated by the WK team based on the task progress.
TOTAL WK SCORE (OUT OF 100%)
WK team: choose Completed, In Progress or Open. Scores calculate from assigned weights; a blank status is not assessed.
05 / WORK ORDER SUMMARY — SAIL PMS
Measure | WO count | Status | Updated | Notes
Generated till now | 4820 | In Progress | 2026-09-29 | The WO will be automatically generated based on the maker manual interval configured in the SAIL system.
Due | 225 | In Progress | 2026-09-29 | The WO will be automatically generated based on the maker manual interval configured in the SAIL system.
Overdue | 198 | In Progress | 2026-09-29 | The WO will be automatically generated based on the maker manual interval configured in the SAIL system.
Active | 214 | In Progress | 2026-09-29 | The WO will be automatically generated based on the maker manual interval configured in the SAIL system.
Pending approval | 151 | In Progress | 2026-09-29 | The WO will be automatically generated based on the maker manual interval configured in the SAIL system.
Completed | 4032 | Completed | 2026-09-29 | The WO will be automatically generated based on the maker manual interval configured in the SAIL system.
Counts may overlap: one job can generate multiple work orders over several cycles.
06 / VESSEL ACTION — RUNNING-HOURS DETAILS
Machinery scope | RH machinery created | Vessel RH details updated | RH details pending | Updated % | Status | Updated | Target | Notes
RH Machinery | 41 | 30 |  |  | Pending Wah Kwong Action |  |  | The vessel needs to update the Running Hours (RH) for 11 machinery.
Created = RH machinery in scope. Updated = records with vessel-entered hours. Pending and percentage calculate from confirmed counts.
Set reporting details on Dashboard. Confirm quantities with source owners before sharing; this workbook is not connected to live SAIL PMS data.
Note on AA6: Hidden rough-estimate denominators used by the weighted progress formulas. Update only when the baseline is confirmed.
Note on M21: Existing estimated critical-item baselines retained only for the receipt KPI and chart; not displayed or printed.
Note on AA21: Hidden rough-estimate denominators used by the critical-item formulas. Update only when the baseline is confirmed.
Note on M22: Existing baseline retained for critical receipt calculations; confirm with WK before treating as final.
Note on M23: Existing baseline retained for critical receipt calculations; confirm with WK before treating as final.
Note on M24: Existing baseline retained for critical receipt calculations; confirm with WK before treating as final.